## Process overview
PROCESS OVERVIEW - prepared by 9teams, awesome collaboration for ERP teams
RASCI SUMMARY
[8 empty] | Production | [10 empty] | Packing | [11 empty] | Warehousing and Shipping |  |  |  |  | Procurement |  |  | PackMat |  | Sales |  | Sales Backoffice | [8 empty] | Transport |  | QA |  |  |  | Accounting | [7 empty] | Controlling |  | Maintenance | [13 empty] | Totals
| Process Domain Process Process Area |  |  | Training wave | SAP process owner | SAP trainer | Business process owner | PR 1 | PR 2 | PR 3 | PR 4 | PR 5 | PR 6 | PR 7 | PR 8 | PR 9 | PR 10 | PR 11 | PA 1 | PA 2 | PA 3 | PA 4 | PA 5 | PA 6 | PA 7 | PA 8 | PA 9 | PA 10 | PA 11 | PA 12 | WS 1 | WS 2 | WS 3 | WS 4 | WS 5 | PO 1 | PO 2 | PO 3 | MA 1 | MA 2 | SA 1 | SA 2 | BO 1 | BO 2 | BO 3 | BO 4 | BO 5 | BO 6 | BO 7 | BO 8 | BO 9 | TR 1 | TR 2 | QA 1 | QA 2 | QA 3 | QA 4 | AC 1 | AC 2 | AC 3 | AC 4 | AC 5 | AC 6 | AC 7 | AC 8 | CO 1 | CO 2 | PM 1 | PM 2 | PM 3 | PM 4 | PM 5 | PM 6 | PM 7 | PM 8 | PM 9 | Accountable | Responsible | Supportive | Consulted | Informed | Total | Trained
[8 empty] | 8 | 8 | 4 | 6 | 6 | 4 | 4 | 4 | 6 | 0 | 0 | 33 | 2 | 11 | 22 | 11 | 11 | 3 | 2 | 7 | 1 | 3 | 0 | 9 | 14 | 10 | 10 | 0 | 9 | 9 | 0 | 0 | 0 | 1 | 1 | 22 | 9 | 8 | 8 | 8 | 8 | 8 | 10 | 8 | 3 | 0 | 3 | 3 | 0 | 3 | 9 | 7 | 3 | 9 | 0 | 4 | 3 | 0 | 0 | 0 | 17 | 2 | 16 | 3 | 3 | 2 | 1 | 2 | 0 | A | R | S | C | I
|  | Training code | Training description | Wave | Owner | , | ,
x | I - | GENERAL PROCESSES
x
x
x | II - | INBOUND PROCESSES
x |  | IB01 | Material requirements planning for procurement | Wave 2 | SAP Owner 1 | SAP trainer 1 | BPO 1 | Production PR 1: A; Production PR 2: R; Packing PA 1: S; Procurement PO 1: A; Procurement PO 2: R; Sales Backoffice BO 1: A; Maintenance PM 1: A; Maintenance PM 3: R | 4 | 3 | 1 | 0 | 0 | 8 | 8
x |  | IB02 | Call-off of WM goods with an external supplier | Wave 1 | SAP Owner 2 | SAP trainer 1 | BPO 2 | Procurement PO 1: A; Procurement PO 2: R; Sales Backoffice BO 1: C; Sales Backoffice BO 2: R; Maintenance PM 1: A; Maintenance PM 3: R | 2 | 3 | 0 | 1 | 0 | 6 | 5
x |  | IB03 | Receiving WM goods (type 1) | Wave 1 | SAP Owner 1 | SAP trainer 1 | BPO 5 | [69 empty] | 1 | 7 | 0 | 0 | 0 | 8 | 8 | bar: Packing PA 1; Packing PA 4 to Packing PA 6; Warehousing and Shipping WS 1 to Warehousing and Shipping WS 4
x |  | IB04 | Receiving WM goods (type 2) | Wave 1 | SAP Owner 1 | SAP trainer 1 | BPO 5 | Production PR 1: A; Production PR 2: S; Production PR 3: S; Production PR 4: S; Production PR 5: S; Production PR 6: S; Production PR 7: S; Production PR 8: S; Production PR 9: R; Packing PA 1: A; Packing PA 4: R | 2 | 2 | 7 | 0 | 0 | 11 | 11
x |  | IB05 | Call-off of IM goods with an external supplier | Wave 1 | SAP Owner 2 | SAP trainer 1 | BPO 2 | Procurement PO 1: A; Procurement PO 2: R; Sales Backoffice BO 1: C; Sales Backoffice BO 2: R; Maintenance PM 1: A; Maintenance PM 3: R | 2 | 3 | 0 | 1 | 0 | 6 | 5
x |  | IB06 | Receiving IM goods | Wave 1 | SAP Owner 2 | SAP trainer 1 | BPO 5 | [69 empty] | 2 | 2 | 0 | 0 | 0 | 4 | 4 | bar: Packing PA 1; Packing PA 9; Maintenance PM 1; Maintenance PM 3
x |  | IB07 | Accounts Payable PO flow | Wave 2 | SAP Owner 2 | SAP trainer 2 | BPO 6 | [69 empty] | 1 | 5 | 0 | 0 | 0 | 6 | 6 | bar: Accounting AC 1 to Accounting AC 4; Accounting AC 6 to Accounting AC 7
x |  | IB09 | Return to vendor | - | SAP Owner 1 | SAP trainer 3 | BPO 2 | Production PR 1: A; Production PR 2: R; Packing PA 1: A; Packing PA 2: R; Procurement PO 1: A; Procurement PO 2: R; Sales Backoffice BO 1: C; Sales Backoffice BO 2: R; Maintenance PM 1: A; Maintenance PM 3: R | 4 | 5 | 0 | 1 | 0 | 10 | 9
x |  | IB10 | Shipping returned goods | - | SAP Owner 1 | SAP trainer 3 | BPO 5 | Production PR 1: A; Production PR 2: S; Production PR 3: S; Production PR 4: S; Production PR 5: S; Production PR 6: S; Production PR 7: S; Production PR 8: S; Production PR 9: R; Packing PA 1: A; Packing PA 3: S; Packing PA 4: R; Packing PA 5: R; Packing PA 6: R; Warehousing and Shipping WS 1: S; Warehousing and Shipping WS 2: R; Warehousing and Shipping WS 3: R; Warehousing and Shipping WS 4: R; Maintenance PM 1: A; Maintenance PM 3: R | 3 | 8 | 9 | 0 | 0 | 20 | 20
x |  | IB11 | Commercial agreements for procurement | Wave 3 | SAP Owner 2 | SAP trainer 3 | BPO 2 | [69 empty] | 2 | 2 | 0 | 0 | 0 | 4 | 4 | bar: Procurement PO 1 to Procurement PO 2; Maintenance PM 1; Maintenance PM 3
x |  | IB12 | Purchasing reporting | Wave 3 | SAP Owner 2 | SAP trainer 8 | BPO 2 | [69 empty] | 2 | 4 | 0 | 0 | 0 | 6 | 6 | bar: Packing PA 1; Procurement PO 1 to Procurement PO 2; Sales Backoffice BO 1; Maintenance PM 1; Maintenance PM 3
x |  | IB14 | Confirming and creating inbound deliveries | Wave 1 | SAP Owner 2 | SAP trainer 3 | BPO 2 | [69 empty] | 1 | 2 | 0 | 0 | 0 | 3 | 3 | bar: Procurement PO 1 to Procurement PO 2; Sales Backoffice BO 2
x |  | IB15 | Purchase orders for sundry items | Wave 3 | SAP Owner 2 | SAP trainer 8 | BPO 6
x |  | IB16 | Vendor management | Wave 3 | SAP Owner 2 | SAP trainer 3 | BPO 2 | [69 empty] | 1 | 4 | 0 | 0 | 0 | 5 | 5 | bar: Procurement PO 1 to Procurement PO 2; Accounting AC 1 to Accounting AC 2; Accounting AC 4
x |  | IB17 | Receiving WM goods (type 3) | Wave 2 | SAP Owner 1 | SAP trainer 3 | BPO 5 | Packing PA 1: A; Packing PA 3: S; Packing PA 4: R; Packing PA 5: R; Packing PA 6: R; Warehousing and Shipping WS 1: S; Warehousing and Shipping WS 2: R; Warehousing and Shipping WS 3: R; Warehousing and Shipping WS 4: R | 1 | 6 | 2 | 0 | 0 | 9 | 9
x
x | III - | PLANNING AND PRODUCTION PROCESSES
x |  | PP01 | Basic flows on process orders | Wave 2 | SAP Owner 1 | SAP trainer 3
x |  | PP02 | Mid term planning (3w) and MRP | Wave 2 | SAP Owner 1 | SAP trainer 8 | BPO 1 | Packing PA 1: S; Packing PA 4: S; Sales Backoffice BO 1: A; Sales Backoffice BO 2: R | 1 | 1 | 2 | 0 | 0 | 4 | 4
x |  | PP03 | Short term planning, scheduling and sequencing (1w) | Wave 2 | SAP Owner 1 | SAP trainer 8 | BPO 1 | Packing PA 1: S; Packing PA 4: S; Sales Backoffice BO 1: A; Sales Backoffice BO 2: R | 1 | 1 | 2 | 0 | 0 | 4 | 4
x |  | PP04 | Supply of components (frozen) | Wave 2 | SAP Owner 1 | SAP trainer 3 | BPO 5 | Packing PA 1: A; Packing PA 3: S; Packing PA 4: R; Packing PA 5: R; Packing PA 6: R; Packing PA 9: R | 1 | 4 | 1 | 0 | 0 | 6 | 6
x |  | PP05 | Supply of components (seasoning) | Wave 2 | SAP Owner 1 | SAP trainer 3 | BPO 5 | Production PR 1: A; Production PR 2: S; Production PR 3: S; Production PR 4: S; Production PR 5: S; Production PR 6: S; Production PR 7: S; Production PR 8: S; Production PR 9: R; Packing PA 1: A; Packing PA 3: S; Packing PA 9: R | 2 | 2 | 8 | 0 | 0 | 12 | 12
x |  | PP06 | Supply of components (film and carton) | Wave 2 | SAP Owner 1 | SAP trainer 3 | BPO 5 | Packing PA 1: A; Packing PA 3: S; Packing PA 9: R | 1 | 1 | 1 | 0 | 0 | 3 | 3
x |  | PP07 | Consumption of WM components | Wave 3 | SAP Owner 1 | SAP trainer 3 | BPO 5 | Production PR 1: A; Production PR 2: R; Production PR 4: R; Production PR 5: R; Production PR 9: R; Packing PA 1: A; Packing PA 2: S; Packing PA 7: R; Packing PA 10: R; Packing PA 11: R | 2 | 7 | 1 | 0 | 0 | 10 | 10
x |  | PP08 | Pallet labeling and receipt confirmation | Wave 3 | SAP Owner 1 | SAP trainer 3 | BPO 5 | [69 empty] | 2 | 7 | 0 | 0 | 0 | 9 | 9 | bar: Production PR 1 to Production PR 2; Production PR 4 to Production PR 5; Production PR 9; Packing PA 1; Packing PA 7 to Packing PA 8; Packing PA 11
x |  | PP09 | Pallet putaway | Wave 3 | SAP Owner 1 | SAP trainer 3 | BPO 5 | [69 empty] | 1 | 6 | 0 | 0 | 0 | 7 | 7 | bar: Packing PA 1; Packing PA 4; Packing PA 7 to Packing PA 8; Warehousing and Shipping WS 2 to Warehousing and Shipping WS 4
x |  | PP12 | Putaway in warehouse of components (WM goods) | Wave 2 | SAP Owner 1 | SAP trainer 3 | BPO 5 | Production PR 1: A; Production PR 2: S; Production PR 3: S; Production PR 4: S; Production PR 5: S; Production PR 6: S; Production PR 7: S; Production PR 8: S; Production PR 9: R; Packing PA 1: A; Packing PA 4: R; Packing PA 5: R; Packing PA 6: R; Packing PA 9: R | 2 | 5 | 7 | 0 | 0 | 14 | 14
x |  | PP13 | Process order evaluation and closing | Wave 2 | SAP Owner 1 | SAP trainer 8 | BPO 1 | [69 empty] | 2 | 1 | 0 | 0 | 0 | 3 | 3 | bar: Packing PA 1; Sales Backoffice BO 1 to Sales Backoffice BO 2
x |  | PP14 | PP related master data | Wave 2 | SAP Owner 1 | SAP trainer 3 | BPO 1 | [69 empty] | 1 | 2 | 0 | 0 | 0 | 3 | 3 | bar: Sales Backoffice BO 1 to Sales Backoffice BO 2; Sales Backoffice BO 8
x |  | PP15 | Consumption of IM components | - | SAP Owner 1 | - | BPO 5 | [69 empty] | 1 | 0 | 1 | 0 | 0 | 2 | 2 | bar: Packing PA 1; Packing PA 11
x
x
x | IV - | OUTBOUND PROCESSES
x |  | OB01 | Management of sales forecast | Wave 1 | SAP Owner 2 | SAP trainer 4 | BPO 1 | [69 empty] | 1 | 1 | 0 | 0 | 0 | 2 | 2 | bar: Sales Backoffice BO 1; Sales Backoffice BO 8
x |  | OB02 | Sales order entry | Wave 1 | SAP Owner 2 | SAP trainer 4 | BPO 1 | [69 empty] | 1 | 7 | 0 | 0 | 0 | 8 | 8 | bar: Sales Backoffice BO 1; Sales Backoffice BO 3 to Sales Backoffice BO 9
x |  | OB03 | Transport organisation | Wave 1 | SAP Owner 2 | SAP trainer 4 | BPO 1 | [69 empty] | 1 | 1 | 0 | 0 | 0 | 2 | 2 | bar: Sales Backoffice BO 1; Transport TR 1
x |  | OB04 | Organise preparation and loading (stock management) | Wave 3 | SAP Owner 1 | SAP trainer 3 | BPO 5 | Packing PA 1: A; Packing PA 4: R; Packing PA 5: R; Packing PA 6: R; Warehousing and Shipping WS 1: S; Warehousing and Shipping WS 2: R; Warehousing and Shipping WS 3: R; Warehousing and Shipping WS 4: R | 1 | 6 | 1 | 0 | 0 | 8 | 8
x |  | OB06 | Sales Invoicing | Wave 2 | SAP Owner 2 | SAP trainer 4 | BPO 1 | [69 empty] | 1 | 7 | 0 | 0 | 0 | 8 | 8 | bar: Sales Backoffice BO 1; Sales Backoffice BO 3 to Sales Backoffice BO 9
x |  | OB07 | Accounts receivable (OB07(1) & OB07(2)) | Wave 3 | SAP Owner 2 | SAP trainer 2 | BPO 6 | [69 empty] | 2 | 2 | 0 | 0 | 0 | 4 | 4 | bar: Sales Backoffice BO 1; Accounting AC 1 to Accounting AC 2; Accounting AC 4
x |  | OB08 | EDI (sales orders) | Wave 1 | SAP Owner 2 | SAP trainer 4 | BPO 1 | [69 empty] | 1 | 7 | 0 | 0 | 0 | 8 | 8 | bar: Sales Backoffice BO 1; Sales Backoffice BO 3 to Sales Backoffice BO 9
x |  | OB10 | EDI (invoices) | Wave 2 | SAP Owner 2 | SAP trainer 4 | BPO 1 | [69 empty] | 1 | 7 | 0 | 0 | 0 | 8 | 8 | bar: Sales Backoffice BO 1; Sales Backoffice BO 3 to Sales Backoffice BO 9
x |  | OB12 | Consignment replenishment/issue orders | Wave 2 | SAP Owner 2 | SAP trainer 4 | BPO 1 | [69 empty] | 1 | 7 | 0 | 0 | 0 | 8 | 8 | bar: Sales Backoffice BO 1; Sales Backoffice BO 3 to Sales Backoffice BO 9
x |  | OB13 | Return orders | Wave 1 | SAP Owner 2 | SAP trainer 4 | BPO 1 | [69 empty] | 1 | 7 | 0 | 0 | 0 | 8 | 8 | bar: Sales Backoffice BO 1; Sales Backoffice BO 3 to Sales Backoffice BO 9
x |  | OB14 | Receiving return orders | - | SAP Owner 1 | SAP trainer 3 | BPO 5 | Packing PA 1: A; Packing PA 4: R; Packing PA 5: R; Packing PA 6: R; Warehousing and Shipping WS 1: S; Warehousing and Shipping WS 2: R; Warehousing and Shipping WS 3: R; Warehousing and Shipping WS 4: R | 1 | 6 | 1 | 0 | 0 | 8 | 8
x |  | OB15 | Price corrections and debit orders | Wave 1 | SAP Owner 2 | SAP trainer 4 | BPO 1 | [69 empty] | 1 | 7 | 0 | 0 | 0 | 8 | 8 | bar: Sales Backoffice BO 1; Sales Backoffice BO 3 to Sales Backoffice BO 9
x |  | OB16 | Master data for transport management | Wave 1 | SAP Owner 2 | SAP trainer 4 | BPO 1 | [69 empty] | 1 | 1 | 0 | 0 | 0 | 2 | 2 | bar: Sales Backoffice BO 1; Transport TR 1
x |  | OB17 | Commercial agreements and master data for sales | Wave 2 | SAP Owner 2 | SAP trainer 4 | BPO 1 | Procurement PO 1: A; Sales SA 1: A; Sales SA 2: R; Sales Backoffice BO 1: C; Sales Backoffice BO 3: R; Sales Backoffice BO 4: R; Sales Backoffice BO 5: R; Sales Backoffice BO 6: R; Sales Backoffice BO 7: R; Sales Backoffice BO 8: R; Sales Backoffice BO 9: R | 2 | 8 | 0 | 1 | 0 | 11 | 10
x |  | OB18 | Organise preparation and loading (stock management) | Wave 2 | SAP Owner 1 | SAP trainer 3 | BPO 5 | Packing PA 1: A; Packing PA 3: R; Packing PA 4: R; Packing PA 5: R; Packing PA 6: R; Warehousing and Shipping WS 1: S; Warehousing and Shipping WS 2: R; Warehousing and Shipping WS 3: R; Warehousing and Shipping WS 4: R | 1 | 7 | 1 | 0 | 0 | 9 | 9
x
x
x | V - | TRANSFERS BETWEEN PLANTS
x |  | TS01 | Stock transport orders for IM/WM goods | Wave 1 | SAP Owner 2 | SAP trainer 4 | BPO 1 | [69 empty] | 1 | 4 | 0 | 0 | 0 | 5 | 5 | bar: Packing PA 1; Packing PA 4; Procurement PO 2; Sales Backoffice BO 1 to Sales Backoffice BO 2
x |  | TS02 | Transport organisation for stock transport orders | Wave 1 | SAP Owner 2 | SAP trainer 4 | BPO 1 | [69 empty] | 0 | 3 | 0 | 0 | 0 | 3 | 3 | bar: Packing PA 1; Packing PA 4; Transport TR 1
x |  | TS03 | Organise preparation and loading for WM goods on STO | Wave 3 | SAP Owner 1 | SAP trainer 3 | BPO 5 | Packing PA 1: A; Packing PA 3: S; Packing PA 4: R; Packing PA 5: R; Packing PA 6: R; Warehousing and Shipping WS 1: S; Warehousing and Shipping WS 2: R; Warehousing and Shipping WS 3: R; Warehousing and Shipping WS 4: R | 1 | 6 | 2 | 0 | 0 | 9 | 9
x |  | TS04 | Organise preparation and loading for IM goods on STO | Wave 3 | SAP Owner 1 | SAP trainer 3 | BPO 5 | Packing PA 1: A; Packing PA 3: S; Packing PA 9: R | 1 | 1 | 1 | 0 | 0 | 3 | 3
x |  | TS05 | Receiving WM goods on STO (receiving plant) | Wave 1 | SAP Owner 1 | SAP trainer 3 | BPO 5 | Packing PA 1: A; Packing PA 3: ?; Packing PA 4: R; Packing PA 5: R; Packing PA 6: R; Warehousing and Shipping WS 1: S; Warehousing and Shipping WS 2: R; Warehousing and Shipping WS 3: R; Warehousing and Shipping WS 4: R | 1 | 6 | 1 | 0 | 0 | 8 | 8
x |  | TS06 | Receiving IM goods on STO (receiving plant) | Wave 1 | SAP Owner 1 | SAP trainer 3 | BPO 5 | Packing PA 1: A; Packing PA 3: ?; Packing PA 4: R; Packing PA 9: R | 1 | 2 | 0 | 0 | 0 | 3 | 3
x |  | TS07 | Transport costing | Wave 1 | SAP Owner 2 | SAP trainer 4 | BPO 1
x |  | TS08 | Receiving WM goods on STO (receiving plant) | Wave 2 | SAP Owner 1 | SAP trainer 3 | BPO 5 | Packing PA 1: A; Packing PA 3: R; Packing PA 4: R; Packing PA 5: R; Packing PA 6: R; Warehousing and Shipping WS 1: S; Warehousing and Shipping WS 2: R; Warehousing and Shipping WS 3: R; Warehousing and Shipping WS 4: R | 1 | 7 | 1 | 0 | 0 | 9 | 9
x
x
x | VI - | WAREHOUSE INTERNAL PROCESSES
x |  | WH01 | Transfer restriction code (storage location) on HU level | Wave 1 | SAP Owner 1 | SAP trainer 5 | BPO 4 | [69 empty] | 1 | 2 | 0 | 0 | 0 | 3 | 3 | bar: QA QA 1 to QA QA 2; QA QA 4
x |  | WH03 | Move pallets between storage bins | Wave 1 | SAP Owner 1 | SAP trainer 5 | BPO 5 | [69 empty] | 1 | 2 | 0 | 0 | 0 | 3 | 3 | bar: Packing PA 1; Packing PA 4; Warehousing and Shipping WS 2
x |  | WH04 | Change stock on a handling unit | Wave 1 | SAP Owner 1 | SAP trainer 5 | BPO 5 | [69 empty] | 1 | 2 | 0 | 0 | 0 | 3 | 3 | bar: Packing PA 1; Packing PA 4; Warehousing and Shipping WS 2
x |  | WH05 | Stock reporting | Wave 2 | SAP Owner 1 | SAP trainer 5 | BPO 5 | [69 empty] | 1 | 5 | 0 | 0 | 0 | 6 | 6 | bar: Packing PA 1; Packing PA 4; Warehousing and Shipping WS 2; QA QA 1 to QA QA 2; QA QA 4
x |  | WH06 | Traceability reporting & batch management | Wave 2 | SAP Owner 1 | SAP trainer 5 | BPO 4 | [69 empty] | 1 | 2 | 0 | 0 | 0 | 3 | 3 | bar: QA QA 1 to QA QA 2; QA QA 4
x |  | WH09 | Warehouse exception handling procedures | Wave 2 | SAP Owner 1 | SAP trainer 5 | BPO 5 | [69 empty] | 1 | 2 | 0 | 0 | 0 | 3 | 3 | bar: Packing PA 1; Packing PA 4; Warehousing and Shipping WS 2
x
x
x | VII - | FINANCIAL PROCESSES
x |  | FI00 | Finance general SAP introduction training | - |  |  | BPO 6
x |  | FI01 | Fixed Assets (direct capitalisation) | - | SAP Owner 2 | SAP trainer 2 | BPO 6
x |  | FI02 | General Ledger | Wave 1 | SAP Owner 2 | SAP trainer 2 | BPO 6 | [69 empty] | 1 | 5 | 0 | 0 | 0 | 6 | 6 | bar: Accounting AC 1 to Accounting AC 4; Accounting AC 6 to Accounting AC 7
x |  | FI03 | Fixed Assets (investment orders) | Wave 3 | SAP Owner 2 | SAP trainer 2 | BPO 6 | [69 empty] | 1 | 2 | 0 | 0 | 0 | 3 | 3 | bar: Accounting AC 1; Accounting AC 4; Accounting AC 6
x |  | FI04 | Accounts Payable outgoing payments + clearing | Wave 2 | SAP Owner 2 | SAP trainer 2 | BPO 6 | [69 empty] | 1 | 2 | 0 | 0 | 0 | 3 | 3 | bar: Accounting AC 1 to Accounting AC 2; Accounting AC 4
x |  | FI05 | Accounts Payable non po flow | Wave 2 | SAP Owner 2 | SAP trainer 2 | BPO 6 | [69 empty] | 1 | 5 | 0 | 0 | 0 | 6 | 6 | bar: Accounting AC 1 to Accounting AC 4; Accounting AC 6 to Accounting AC 7
x |  | FI06 | Credit management | Wave 3 | SAP Owner 2 | SAP trainer 2 | BPO 6 | [69 empty] | 1 | 2 | 0 | 0 | 0 | 3 | 3 | bar: Accounting AC 1 to Accounting AC 2; Accounting AC 4
x |  | FI07 | Period end closure + VAT reports | Wave 1 | SAP Owner 2 | SAP trainer 2 | BPO 6 | [69 empty] | 1 | 1 | 0 | 0 | 0 | 2 | 2 | bar: Accounting AC 1; Accounting AC 4
x
x | VIII - | CONTROLLING PROCESSES
x |  | CO01 | Profit Center and cost center accounting | Wave 2 | SAP Owner 2 | SAP trainer 6 | BPO 6
x |  | CO02 | Assessment on cost center | Wave 2 | SAP Owner 2 | SAP trainer 6 | BPO 6
x
x | IIX - | MAINTENANCE PROCESSES
x |  | PM01 | Maintenance of functional locations | Wave 2 | SAP Owner 2 | SAP trainer 7 | BPO 3 | [69 empty] | 1 | 2 | 0 | 0 | 0 | 3 | 3 | bar: Maintenance PM 1 to Maintenance PM 3
x |  | PM11 | Crash order (incl. corrections) | Wave 2 | SAP Owner 2 | SAP trainer 7 | BPO 3 | [69 empty] | 1 | 6 | 0 | 0 | 0 | 7 | 7 | bar: Maintenance PM 1; Maintenance PM 3 to Maintenance PM 8
|  | PM11 |  | Wave 2 |  | SAP trainer 7 | BPO 3 | bar: Maintenance PM 2; Maintenance PM 4 to Maintenance PM 5
x |  | PM12 | Close maintenance order | Wave 2 | SAP Owner 2 | SAP trainer 7 | BPO 3 | [69 empty] | 1 | 0 | 0 | 0 | 0 | 1 | 1 | bar: Maintenance PM 1
x |  | PM13 | Reporting on maintance orders | Wave 2 | SAP Owner 2 | SAP trainer 7 | BPO 3 | [69 empty] | 1 | 5 | 0 | 0 | 0 | 6 | 6 | bar: Maintenance PM 1; Maintenance PM 3 to Maintenance PM 6; Maintenance PM 8
x |  | PM21 | Call-off of spare parts with an external supplier (IB05) | Wave 1 | SAP Owner 2 | SAP trainer 7 | BPO 3 | [69 empty] | 1 | 1 | 0 | 0 | 0 | 2 | 2 | bar: Maintenance PM 1; Maintenance PM 3
x |  | PM22 | Receiving spare parts (IB06) | Wave 1 | SAP Owner 2 | SAP trainer 7 | BPO 3 | [69 empty] | 1 | 1 | 0 | 0 | 0 | 2 | 2 | bar: Maintenance PM 1; Maintenance PM 3
x |  | PM23 | Stock corrections and management of spare parts (WH05) | Wave 2 | SAP Owner 1 | SAP trainer 7 | BPO 3 | [69 empty] | 1 | 1 | 0 | 0 | 0 | 2 | 2 | bar: Maintenance PM 1; Maintenance PM 3
x |  | PM24 | Purchasing reporting (IB12) | Wave 3 | SAP Owner 2 | SAP trainer 7 | BPO 3 | [69 empty] | 1 | 1 | 0 | 0 | 0 | 2 | 2 | bar: Maintenance PM 1; Maintenance PM 3
x |  | PM31 | Material requirements planning for spare parts (IB01) | Wave 2 | SAP Owner 1 | SAP trainer 7 | BPO 3 | [69 empty] | 1 | 1 | 0 | 0 | 0 | 2 | 2 | bar: Maintenance PM 1; Maintenance PM 3
x

## RASCI matrix
1
RASCI Overview
| Code | Description | Training? | Explanation
| R | Responsible | Yes | that is the person who is owner of the process
| A | Accountable | Yes | that is the person to whom "R" is Accountable and is the authority who approves to sign off on work before it is effective. A is the owner of the process. If A is not defined, this means that R also takes up the role of A.
| S | Supportive | Yes (limited) | that is a person who plays a supporting role in the process
| C | Consulted | No | that is a person who provides information and/or expertise necessary to complete the process
| I | Informed | No | that is a person who needs to be notified of results but need not necessarily be consulted

## Selections
Status | Status | Présence | Importance | Action | Status 2 | Status 3 | Scope
1. Preparation | R | N/A | ▲ | Prep | 1. New | 1. To do | PL
2. To do | A | Opt | ► | Align | 2. Open | 2. Consultant alignment | DA
3. In progress | S | Man | ▼ | Other | 3. In progress | 3. Preparation | EL
4. Session | C |  |  |  | 4. Prepared | 4. Session | LI
5. Validation | I |  |  |  | 5. Approved | 5. Validation | AD
6. Done |  |  |  |  | 6. Closed | 6. Done | WA
7. Rework |  |  |  |  | 7. Rework | 7. Rework
N/A |  |  |  |  | N/A | N/A